TERTIARY REVIEW OF QUALIFICATIONS

MASSAGE THERAPY

REVIEW PLAN

Version 1

Contents

A	Purpose	3

B	Objectives	3

C	Scope	3

D	Stakeholders	4

E	Structure and Process	5

F	Timelines & deliverables	5

G	Roles & responsibilities	6

G.1	How work will be undertaken	6

G.2	How decisions will be made	6

H	Resources & how cost of review will be met	7

I	Risks that may impact on review	7

I.1	Key Risks	7

I.2	Risk Management	7

J	Outline of approach	7

J.1	Identifying wider sector/industry/community workforce needs	8

J.2	Assessing need & demand for current qualifications	8

J.3	Addressing any issues of duplication &/or proliferation	8

J.4	Involving & consulting with appropriate stakeholders	8

J.5	Communicating with all stakeholders	8

Report Prepared by:

TRoQ – Massage Therapy Governance Group

Date

REVIEW PLAN FOR TERTIARY REVIEW OF QUALIFICATIONS - MASSAGE THERAPY

# Purpose

The purpose of this plan is to document the planned approach to the Mandatory Review of Massage Therapy qualifications triggered on 10 December 2012.

# Objectives

Collaboratively determine the suite of qualifications needed to meet current and future needs of stakeholders and identify areas or gaps for development.

Develop robust and credible graduate profiles that are consistent with stakeholder needs, roles, role pathways, and levels.

Submit the outcome of the review and its recommendations for New Zealand Qualifications Authority (NZQA) approval.

# Scope

The review will develop a framework for Massage Therapy qualifications in accordance with NZQA’s Requirements for listing and maintaining qualification on the New Zealand Qualifications Framework (V.2.0, April 2011).

The scope of the review includes those qualifications listed in the table below.

Add Swedish Massage qual

| Provider Name | Qualification Title |
| --- | --- |
| Institute of Technology or Polytechnic |
| Bay of Plenty Polytechnic | Certificate in Relaxation Massage Level 4 |
| EIT | Certificate in Sport and Health Massage |
|  | Diploma in Therapeutic and Sport Massage |
|  | National Certificate in Massage (Relaxation Massage) Level 4 |
| NorthTec | Diploma in Massage |
|  | Northland Polytechnic Certificate in Relaxation Massage |
| Otago Polytechnic | Certificate in Relaxation Massage (Level 4) |
|  | Certificate in Stress Management and Spa Therapies (Level 5) |
|  | Diploma in Advanced Therapeutic Massage (Level 6) |
| SIT | Bachelor of Therapeutic and Sports Massage |
|  | Certificate in Massage (Massage Relaxation)(Level 4) |
|  | Diploma in Therapeutic and Sports Massage |
| UCOL | Certificate in Relaxation Massage |
|  | Certificate in Therapeutic Massage |
|  | Diploma in Applied Massage Therapies, Level 6 |
| Waiariki Institute of Technology | Diploma in Spa and Body Therapies |
|  | Diploma in Therapeutic Massage and Spa |
| Private Training Establishment |
| Canterbury College of Natural Medicine | Diploma In Massage Therapy |
| Fashion and Faces International | National Certificate in Massage (Relaxation Massage) (Level 4) |
| Lotus Holistic Centre | Certificate in Massage Modalities |
|  | Certificate in Wellness Massage |
|  | Diploma in Therapeutic Massage |
| Naturopathic College of New Zealand | Certificate in Massage (Relaxation Massage) (Level |
|  | Diploma in Remedial Body Therapies |
|  | National Diploma of Massage (Therapeutic Massage) |
| New Zealand School of Education Limited | Diploma In Massage Therapy |
| NZ College of Massage | Bachelor of Health Studies (Massage and Neuromuscular Therapy) |
|  | Certificate in Relaxation Massage |
|  | Diploma in Health Sciences (Massage and Sports Therapy) |
|  | Diploma in Health Sciences (Therapeutic Massage) or (Reflexology) Level 6 |
| Wellpark College | Certificate in Relaxation Massage (Level 5) |

# Stakeholders

The table below lists the stakeholders identified for this review.

Insert stakeholder list

# Structure and Process

The review will be led by a Governance Group representing key stakeholder groups. The Governance Group members are listed in the table below.

Do we need an additional member representing Certificate Programmes with Pip no longer employed by Bay of Plenty Polytechnic, or can Donna represent Certificate Programmes?

| Name | Organisation | Representing |
| --- | --- | --- |
| Stephen Burden | Massage New Zealand | Massage therapists in general |
| Iselde de Boam |  | Medium-sized massage business |
| Justine Rutherford, Spa Manager | Hanmer Springs | The spa industry |
| Philip Cottingham | Wellpark College | Complementary Therapies |
| Pip Charlton | High Performance Sport NZ | High performance sport |
| Cathy Allan | Lotus College | Diploma programmes |
| Donna Smith | Southern Institute of Technology / | Certificate programmes? Degree programmes |
| Api Fiso | New Zealand College of Massage | Degree programmes |
|  |  | Academic Manager |
|  |  | Iwi perspective |

The Governance Group will be supported by Leigh Milmine, Sector Relationship Manager, NZQA and Sheryl Smail, Pivotal, Professional Advisor for NZQA.

The role of the Governance Group is to:

- Set direction and approach for the review

- Allocate accountabilities for leading specific review phases or components of the review

- Approve the composition of work groups to undertake the review at the operational level

- Oversee the work and monitor progress of the review

- Make decisions on the new suite of qualifications for submission to NZQA

# Timelines & deliverables

Note: the deliverables below are sourced from NZQA’s GANTT chart ‘Draft Outline of Mandatory Review Key Deliverables and Timeline’ – they have not been considered by the Governance Group.  The GANTT chart also has indicative times for the 6 months that the Governance Group could use as a starting point to determine timelines for the review – a copy of the GANTT chart is attached.

| Deliverable | Timeline |
| --- | --- |
| Stakeholder profile confirmed |  |
| Qualifications included confirmed |  |
| Initial draft of review plan completed |  |
| Stakeholders consulted on draft review plan |  |
| Industry needs analysis completed |  |
| Review plan signed off by Governance Group |  |
| Skills mapped to qualifications |  |
| Draft strategic purpose and outcome statements developed |  |
| Draft suite of new qualifications prepared |  |
| Consultation with stakeholders on new qualifications complete |  |
| Strategic purpose and outcome statements revised |  |
| Governance Group signs off suite of qualifications |  |
| Final consultation completed |  |
| Stakeholder attestations completed |  |
| Qualification owners sign-off on qualifications completed |  |
| Applications for pre-approval and review report prepared |  |
| Applications and report signed off by Governance Group |  |

# Roles & responsibilities

## How work will be undertaken

The Governance Group will take the Review Lead role for this review.  The NZ College of Massage is providing resource support: venue hosting for face to face meetings and coordination for development of the review plan and the communication plan.  Implementation of the review plan will be either undertaken collectively by the Governance Group or delegated to individual governance group members to coordinate.

The operational work for the review will be undertaken by one or more work groups.  The sector has an existing Massage Therapy Education Group (M.E.G.) which has a demonstrated track record of working collaboratively.  M.E.G. has undertaken the preparatory work for this review to date.

The Governance Group is committed to working transparently and collaboratively with stakeholders in the development of the new suite of qualifications.

## How decisions will be made

The Governance Group has agreed to use consensus decision making and has adopted a process for determining consensus.

# Resources & how cost of review will be met

The massage therapy sector is not well resourced to be undertaking this review.  Every effort will be made to keep the direct costs of the review to a minimum.  Costs incurred in undertaking the review and in participation will be borne by the organisation incurring the costs, unless agreed otherwise by the Governance Group in advance of the costs being incurred.

NZQA is funding assistance from the Sector Relationship Manager and Professional Adviser.  They are also providing, at their cost, minute taking and other administrative support.

# Risks that may impact on review

## Key Risks

The Governance Group has identified the key risks as being:

- Time – there is not a designated resource person available to devote substantial time to lead this review

- Cost – the sector does not have an ITO to lead the review, nor are the key stakeholders able to financially resource release of a review lead nor collectively fund an independent review lead.

- Deviation from having a clear open process

- People in the sector not understanding the importance of the TRoQ process and the new qualification suite that will result from the review.

## Risk Management

The Governance Group plans identified the strategies outlined below to manage the key review risks.

- The Governance Group will undertake the Lead Review role, so that the time and costs are spread across members

- Meetings will be held using online or telecommunication meeting technology whenever feasible

- An online central repository will be established for sharing access to review documents and for enabling cost-effective and efficient feedback on draft documents

- At the outset of the review, to disseminate a clear, jargon-free letter to all stakeholders that explains what the mandatory Tertiary Review of Qualifications, its relevance to stakeholders, and why it is important that stakeholders participate in the review.

- Develop and adhere to a Review Communication Plan that supports proactive, low cost communication with all stakeholders and formalises governance group expectations and planned engagement approach.

# Outline of approach

M.E.G did considerable preparatory work before the review was triggered including: initial stakeholder profile prepared; identifying qualifications and resourcing needs analysis information.

## Identifying wider sector/industry/community workforce needs

Next steps to address gaps will need to be added

## Assessing need & demand for current qualifications

## Addressing any issues of duplication &/or proliferation

## Involving & consulting with appropriate stakeholders

The Governance Group plans to take a transparent and collaborative approach to engaging stakeholders.  Steps include:

- Keeping the already established M.E.G. well informed regarding progress and involving members in work groups

- Establishing an online portal where stakeholders can readily access current information about the review

- Optimising efficient use of stakeholder time by:

  - Using focussed questions when seeking input

  - Making effective use of technology to involve stakeholders at minimal or no direct cost to them

## Communicating with all stakeholders

Add key elements of communication plan